## Details
ANALYSISTAB MULTIPLE PROJECTS - GANTT TEMPLATE
Works on Excel 2007 and Above
Info | Project Plan and Gant Chart Template helps you to plan a project timelines and resource. You can change the default data and formula to meet your needs. |  | Please Note: We have protected the worksheets to avoid the mistakes by chance. You can use the password 'PNRao' to unprotect the Worksheets
Usage | We start plannign our projects after initial meetings and agreement. We plan our resource and timelines based on the requirements, deliverables and avaialble team and bandwidth. Project plan template helps to track all the tasks and its progress and status of each task. You can daily update the templates and share with your teams and customer/stakeholders to update the project status and progress. This is the must have tool for every project.
Please Share | Project Tracking/ Project Plan / Gant. Chart Template is a Free and lite version of ANALYSISTABS' Project Management Templates. Please feel free to use, modify and share with your coleagues. | Please check our Premium Templates Bundle, all you need for effective project planning, management and presentations. Our premium templates are professional, powerfull, easy to customize and unique in style. Please visit analysistabs.com and grab our powerfull templates for nominal cost.
Please Let us know your feedback |  |  |  | info@analysistabs.com
Templates By ANALYSISTABS.For more templates and tools, please visit us: |  |  |  | htps://analysistabs.com
Premium Templates
Visit Our BLOG
ANALYSISTABS.COM
Project Gantt. 4
Data Sheet4
Advanced Templates4

## Project Plan
Please Select a Project to View Related Tasks & Gantt. |  |  |  | 4 |  | All Projects | 80 Tasks Found
| Project Plan |  |  | Tasks Scrool | Task ID | TaskS | Responsible | Start Date | End Date | Days Req. | Status | Days Comp. | Project | 2016-02-12 | 2016-02-13 | 2016-02-14 | 2016-02-15 | 2016-02-16 | 2016-02-17 | 2016-02-18 | 2016-02-19 | 2016-02-20 | 2016-02-21 | 2016-02-22 | 2016-02-23 | 2016-02-24 | 2016-02-25 | 2016-02-26 | 2016-02-27
|  |  |  | 0 | 0 | 0 | 1 | 2 | 4 | 3 | 4 |  | -1
Project Name |  |  |  |  | 1 | Task 1 | Person 1 | 2016-02-16 | 2016-02-20 | 5 | 100% | 5 | Project 1
Customer Name |  |  |  |  | 2 | Task 2 | Person 2 | 2016-02-17 | 2016-02-22 | 6 | 100% | 6 | Project 1
Project Manager |  |  |  |  | 3 | Task 3 | Person 3 | 2016-02-18 | 2016-02-27 | 10 | 100% | 10 | Project 1
[5 empty] | 4 | Task 4 | Person 4 | 2016-02-21 | 2016-02-29 | 9 | 100% | 9 | Project 1
Start Date |  | 2016-02-12 |  |  | 5 | Task 5 | Person 5 | 2016-02-17 | 2016-02-20 | 4 | 100% | 4 | Project 1
End Date |  | 2016-03-12 |  |  | 6 | Task 6 | Person 1 | 2016-02-20 | 2016-02-25 | 6 | 100% | 6 | Project 1
Overall Progress |  | 55.07% |  |  | 7 | Task 7 | Person 2 | 2016-02-20 | 2016-02-26 | 7 | 100% | 7 | Project 1
|  | 44.92% |  |  | 8 | Task 8 | Person 3 | 2016-02-22 | 2016-02-26 | 5 | 100% | 5 | Project 1
Days Required 6 |  |  |  |  | 9 | Task 9 | Person 4 | 2016-02-22 | 2016-03-01 | 9 | 100% | 9 | Project 1
29 days |  |  |  |  | 10 | Task 10 | Person 5 | 2016-02-23 | 2016-02-28 | 6 | 100% | 6 | Project 1
532 ManDays |  |  |  |  | 11 | Task 11 | Person 1 | 2016-02-13 | 2016-02-19 | 7 | 59% | 4.13 | Project 2
[5 empty] | 12 | Task 12 | Person 2 | 2016-02-17 | 2016-02-25 | 9 | 41% | 3.69 | Project 2
Gantt. Scroll |  |  | 0 |  | 13 | Task 13 | Person 3 | 2016-02-18 | 2016-02-25 | 8 | 0% | 0 | Project 2
[5 empty] | 14 | Task 14 | Person 4 | 2016-02-20 | 2016-02-26 | 7 | 49% | 3.43 | Project 2
Total Tasks | 80 | Remarks |  |  | 15 | Task 15 | Person 5 | 2016-02-21 | 2016-02-24 | 4 | 36% | 1.44 | Project 2
Not Started(0%) | 2 |  |  |  | 16 | Task 16 | Person 1 | 2016-02-21 | 2016-02-26 | 6 | 54% | 3.24 | Project 2
Inprogress(1-99%) | 58 |  |  |  | 17 | Task 17 | Person 2 | 2016-02-24 | 2016-02-29 | 6 | 57% | 3.42 | Project 2
1-25% | 11 |  |  |  | 18 | Task 18 | Person 3 | 2016-02-25 | 2016-02-28 | 4 | 22% | 0.88 | Project 2
26-50% | 30 |  |  |  | 19 | Task 19 | Person 4 | 2016-02-27 | 2016-03-04 | 7 | 46% | 3.22 | Project 2
51-75% | 15 |  |  |  | 20 | Task 20 | Person 5 | 2016-02-16 | 2016-02-18 | 3 | 100% | 3 | Project 2
76-99% | 2 |  |  |  | 21 | Task 21 | Person 1 | 2016-02-12 | 2016-02-21 | 10 | 100% | 10 | Project 3
Completed(100%) | 20 |  |  |  | 22 | Task 22 | Person 2 | 2016-02-21 | 2016-02-25 | 5 | 100% | 5 | Project 3
[5 empty] | 23 | Task 23 | Person 3 | 2016-02-23 | 2016-02-29 | 7 | 100% | 7 | Project 3
[5 empty] | 24 | Task 24 | Person 4 | 2016-02-26 | 2016-03-03 | 7 | 100% | 7 | Project 3
Project Gantt. Template By: |  | https://analysistabs.com | PNRao |  | 25 | Task 25 | Person 5 | 2016-02-28 | 2016-03-01 | 3 | 100% | 3 | Project 3
Please let us know your feedback ¦ Email: info@analysistabs.com
Task Grid
Gantt Chart
55%

## Projects Summary
Projects | Tasks | Start | End | Days | %Progress | Remaining
All Projects | 80 | 2016-02-12 | 2016-03-12 | 532 | 55.07% | 44.92%
Project 1 | 10 | 2016-02-16 | 2016-03-04 | 67 | 100% | 0%
Project 2 | 10 | 2016-02-13 | 2016-03-07 | 61 | 46.4% | 53.6%
Project 3 | 5 | 2016-02-12 | 2016-03-09 | 32 | 100% | 0%
Project 4 | 7 | 2016-02-16 | 2016-03-12 | 51 | 44.43% | 55.57%
Project 5 | 8 | 2016-02-19 | 2016-03-11 | 55 | 33.88% | 66.12%
Project 6 | 8 | 2016-02-16 | 2016-03-03 | 52 | 63% | 37%
Project 7 | 9 | 2016-02-13 | 2016-03-04 | 62 | 40.56% | 59.44%
Project 8 | 11 | 2016-02-12 | 2016-03-12 | 69 | 47.91% | 52.09%
Project 9 | 4 | 2016-02-19 | 2016-03-06 | 28 | 48.25% | 51.75%
Project 10 | 8 | 2016-02-19 | 2016-03-11 | 55 | 33.88% | 66.12%
Formulas:
Start = MIN(IF('Data Sheet'!$A2:A81=[Projects],'Data Sheet'!$D2:D81))
End = MAX(IF('Data Sheet'!$A2:A81=[Projects],'Data Sheet'!$D2:D81))+MAX(IF('Data Sheet'!$A2:A81=[Projects],'Data Sheet'!$E2:E81))

## Data Sheet
Project | Task | Responsible | Start Date | Days Req. | Progress
Project 1 | Task 1 | Person 1 | 2016-02-16 | 5 | 100%
Project 1 | Task 2 | Person 2 | 2016-02-17 | 6 | 100%
Project 1 | Task 3 | Person 3 | 2016-02-18 | 10 | 100%
Project 1 | Task 4 | Person 4 | 2016-02-21 | 9 | 100%
Project 1 | Task 5 | Person 5 | 2016-02-17 | 4 | 100%
Project 1 | Task 6 | Person 1 | 2016-02-20 | 6 | 100%
Project 1 | Task 7 | Person 2 | 2016-02-20 | 7 | 100%
Project 1 | Task 8 | Person 3 | 2016-02-22 | 5 | 100%
Project 1 | Task 9 | Person 4 | 2016-02-22 | 9 | 100%
Project 1 | Task 10 | Person 5 | 2016-02-23 | 6 | 100%
Project 2 | Task 11 | Person 1 | 2016-02-13 | 7 | 59%
Project 2 | Task 12 | Person 2 | 2016-02-17 | 9 | 41%
Project 2 | Task 13 | Person 3 | 2016-02-18 | 8 | 0%
Project 2 | Task 14 | Person 4 | 2016-02-20 | 7 | 49%
Project 2 | Task 15 | Person 5 | 2016-02-21 | 4 | 36%
Project 2 | Task 16 | Person 1 | 2016-02-21 | 6 | 54%
Project 2 | Task 17 | Person 2 | 2016-02-24 | 6 | 57%
Project 2 | Task 18 | Person 3 | 2016-02-25 | 4 | 22%
Project 2 | Task 19 | Person 4 | 2016-02-27 | 7 | 46%
Project 2 | Task 20 | Person 5 | 2016-02-16 | 3 | 100%
Project 3 | Task 21 | Person 1 | 2016-02-12 | 10 | 100%
Project 3 | Task 22 | Person 2 | 2016-02-21 | 5 | 100%
Project 3 | Task 23 | Person 3 | 2016-02-23 | 7 | 100%
Project 3 | Task 24 | Person 4 | 2016-02-26 | 7 | 100%
Project 3 | Task 25 | Person 5 | 2016-02-28 | 3 | 100%
Project 4 | Task 26 | Person 1 | 2016-03-01 | 9 | 88%
Project 4 | Task 27 | Person 2 | 2016-03-02 | 10 | 20%
Project 4 | Task 28 | Person 3 | 2016-02-16 | 4 | 10%
Project 4 | Task 29 | Person 4 | 2016-02-19 | 8 | 60%
Project 4 | Task 30 | Person 5 | 2016-02-22 | 10 | 34%
Project 4 | Task 31 | Person 1 | 2016-02-25 | 6 | 51%
Project 4 | Task 32 | Person 2 | 2016-02-25 | 4 | 48%
Project 5 | Task 33 | Person 3 | 2016-02-28 | 8 | 32%
Project 5 | Task 34 | Person 4 | 2016-03-01 | 9 | 42%
Project 5 | Task 35 | Person 5 | 2016-02-20 | 5 | 59%
Project 5 | Task 36 | Person 1 | 2016-02-19 | 3 | 31%
Project 5 | Task 37 | Person 2 | 2016-02-21 | 7 | 49%
Project 5 | Task 38 | Person 3 | 2016-02-22 | 10 | 16%
Project 5 | Task 39 | Person 4 | 2016-02-22 | 10 | 31%
Project 5 | Task 40 | Person 5 | 2016-02-22 | 3 | 11%
Project 6 | Task 1 | Person 1 | 2016-02-16 | 5 | 47%
Project 6 | Task 2 | Person 2 | 2016-02-17 | 6 | 43%
Project 6 | Task 3 | Person 3 | 2016-02-18 | 10 | 38%
Project 6 | Task 4 | Person 4 | 2016-02-21 | 9 | 100%
Project 6 | Task 5 | Person 5 | 2016-02-17 | 4 | 100%
Project 6 | Task 6 | Person 1 | 2016-02-20 | 6 | 100%
Project 6 | Task 7 | Person 2 | 2016-02-20 | 7 | 42%
Project 6 | Task 8 | Person 3 | 2016-02-22 | 5 | 34%
Project 7 | Task 9 | Person 4 | 2016-02-22 | 9 | 14%
Project 7 | Task 10 | Person 5 | 2016-02-23 | 6 | 55%
Project 7 | Task 11 | Person 1 | 2016-02-13 | 7 | 59%
Project 7 | Task 12 | Person 2 | 2016-02-17 | 9 | 41%
Project 7 | Task 13 | Person 3 | 2016-02-18 | 8 | 0%
Project 7 | Task 14 | Person 4 | 2016-02-20 | 7 | 49%
Project 7 | Task 15 | Person 5 | 2016-02-21 | 4 | 36%
Project 7 | Task 16 | Person 1 | 2016-02-21 | 6 | 54%
Project 7 | Task 17 | Person 2 | 2016-02-24 | 6 | 57%
Project 8 | Task 18 | Person 3 | 2016-02-25 | 4 | 22%
Project 8 | Task 19 | Person 4 | 2016-02-27 | 7 | 46%
Project 8 | Task 20 | Person 5 | 2016-02-16 | 3 | 100%
Project 8 | Task 21 | Person 1 | 2016-02-12 | 10 | 47%
Project 8 | Task 22 | Person 2 | 2016-02-21 | 5 | 55%
Project 8 | Task 23 | Person 3 | 2016-02-23 | 7 | 38%
Project 8 | Task 24 | Person 4 | 2016-02-26 | 7 | 33%
Project 8 | Task 25 | Person 5 | 2016-02-28 | 3 | 68%
Project 8 | Task 26 | Person 1 | 2016-03-01 | 9 | 88%
Project 8 | Task 27 | Person 2 | 2016-03-02 | 10 | 20%
Project 8 | Task 28 | Person 3 | 2016-02-16 | 4 | 10%
Project 9 | Task 29 | Person 4 | 2016-02-19 | 8 | 60%
Project 9 | Task 30 | Person 5 | 2016-02-22 | 10 | 34%
Project 9 | Task 31 | Person 1 | 2016-02-25 | 6 | 51%
Project 9 | Task 32 | Person 2 | 2016-02-25 | 4 | 48%
Project 10 | Task 33 | Person 3 | 2016-02-28 | 8 | 32%
Project 10 | Task 34 | Person 4 | 2016-03-01 | 9 | 42%
Project 10 | Task 35 | Person 5 | 2016-02-20 | 5 | 59%
Project 10 | Task 36 | Person 1 | 2016-02-19 | 3 | 31%
Project 10 | Task 37 | Person 2 | 2016-02-21 | 7 | 49%
Project 10 | Task 38 | Person 3 | 2016-02-22 | 10 | 16%
Project 10 | Task 39 | Person 4 | 2016-02-22 | 10 | 31%
Project 10 | Task 40 | Person 5 | 2016-02-22 | 3 | 11%

## Advanced Project Plan Template
Ultimate Project Plan Advanced Excel Template
The Most Powerful Project Planning Template on the Market
View Details 4
Our Most Popular Project Management Templates
Excel Templates | PowerPoint Templates | MS Word Templates
Browse All Templates4